## Sprint-Backlog
|  | Current Sprint: Sprint 1 | [7 empty] | Original Date as of 8/26/11
My Status | My Notes | Story # | Priority（1～10） | Area of work/Module | Story Description | Story Points | Team | Creation Start Date Plan | User Story Completion Date | Creation Complete Date Plan | Creation Complete Date Actual | Development Complete Date Plan | Development Complete Date Actual | Testing Complete Date Plan | Testing Complete Date Actual | Status | Arizona vs. California Delta | Arizona Delta | Indiana Delta | Colorado Delta | Notes | Adjusted Story Points | Adjusted AZ SP | Story Points | Development Team | Requirements Type | Proposed Sprint/Fix Version | Quote | New Business (Bind) | New Business Documents | Batch Documents | Efolder Documents | Endorsements | Out of Sequence Endorsments | Cancellation (by insured request or non-pay) | UW requested cancellation | Remove UW requested Cancellation | Reinstate | Systematic Renewal Processing | Renewal Documents | Non-Offer documents | Rewrite / Split / Spin | Billing and Payments | Incoming / Receiving | Outgoing / Providing | Form Description + AZ Form # | Form Name
|  | CM-006 | 9 | 展示模块 | 用户在该界面可以看到现有的健身场馆的信息 | 1 | T4 |  |  | 2011-05-27 | 2011-05-27 |  |  |  |  | Approved | No Delta | No Delta | No Delta | No Delta | NOT DONE | 0 | 0 | 0 |  | 功能性需求：界面会展示出来五个左右的推荐的健身场馆点击详情即可以看到场馆内的详情 非功能性需求：查看场馆的详情跳转时间不能超过2秒 | Sprint 1 | X | X | X
|  | CM-007 | 8 | 展示模块 | 导航栏模块，用户可以根据导航栏的选项进入对应的模块中 | 1 | T4 |  |  | 2011-05-27 | 2011-06-01 |  |  |  |  | Approved | No Delta | No Delta | No Delta | No Delta | NOT DONE | 0 | 0 | 0 |  | 功能性需求：用户点击导航栏上的按钮后，跳转到该功能模块 非功能性需求：点击该功能模块，页面跳转响应时间小于1秒 | Sprint 1 | X | X | X
|  | CM-008 | 5 | 展示模块 | 每个场馆的详情界面的展示 | 1 | T4 |  |  | 2011-05-27 | 2011-05-27 |  |  |  |  | Approved | No Delta | No Delta | No Delta | No Delta | NOT DONE | 0 | 0 | 0 |  | 功能性需求：用户点击场馆的详情，可以看到场馆开放的项目，可以预约的时间，现在的余量、路线、联系电话等信息，且可以对改场馆进行预订 非功能性需求：整个页面的加载时长不能超过3秒，按钮的点击跳转不能超过2秒 | Sprint 1 | X | X | X
|  | CM-009 | 7 | 登录模块 | 用户在该界面登录进入平台 | 1 | T4 |  |  | 2011-05-27 | 2011-06-17 |  |  |  |  | Approved | No Delta | No Delta | No Delta | No Delta | NOT DONE | 0 | 0 | 0 |  | 功能性需求：用户输入用户名和密码以后，如果正确可以 进入平台，不正确弹出响应的提示，是需要注册还是密码不正确 非功能性需求：响应时间不能超过2秒 | Sprint 1 | X | X | X
|  | CM-010 | 6 | 注册模块 | 用户在该界面可以通过手机号进行平台账号的注册 | 6 | T4 |  |  | 2011-05-27 | 2011-05-27 |  |  |  |  | Approved | prefill is required for the common library. This story includes that requirement. | No Delta | No Delta | No Delta | NOT DONE | 3 | 0 | 0 |  | 功能性需求：用户可以通过第三方平台如微信账号进行登录，也可以通过手机号进行注册，发送短信验证即可 非功能性需求：发送短信时长不能超过1分钟，注册时长不能超过5秒。 | Sprint 1 | X | X | X
Note on C3: Elaine Zhao: User Story ID
Note on E3: Elaine Zhao: Sub-category Name
Note on F3: Elaine Zhao: description of User Story
Note on J3: Elaine Zhao: Planned complete date of BA work
Note on Q3: Elaine Zhao: Approval status by customers
Note on V3: Elaine Zhao: User Story completion status
Note on Y3: Elaine Zhao: Story Points
Note on Z3: Elaine Zhao: Team Name that the User stories are assigned to
Note on AA3: Elaine Zhao: Functional Requirement or Non-functional Requirement